## Instructions
AI benefits register
A proposal from AI Economics Hub, version 0.5 (2026-10-08). Not a standard. See the article 'The AI Benefits Register' (/articles/ai-benefits-register).
One row per benefit, not per initiative. An initiative can have several. Cream cells are inputs, grey cells are formulas and are locked. The blue rows are ILLUSTRATIVE, with invented figures: overwrite or delete them.
Money is in £ thousands a year. Expected is the benefit in the business case. Measured is what has been observed. 'Booked in' names the budget line, forecast or accepted record where the benefit shows up.
A benefit counts as realised only if its type is Realised cost reduction, Revenue or margin, or Absorbed capacity, a booked-in record is named, and the evidence level is E2 or above. Released capacity, Avoided cost and Risk loss avoided are reported separately and are never added to realised value.
Released capacity is time freed. It becomes Absorbed capacity only when it has been turned into something an accepted record shows, such as reduced contractor hours or extra throughput.
Sheets are protected without a password so you can unprotect to extend them. Nothing leaves your machine.

## Benefits
ID | Initiative | Benefit | Benefit type | Benefit owner (named role) | Expected annual (£k) | Measured annual (£k) | Booked in (budget line or record) | Evidence level | Status | Variance (£k) | Counts as realised? | Realised value (£k)
ILLUSTRATIVE-B1 | Contract review assistant | Outside-counsel spend reduced | Realised cost reduction | General Counsel | 160 | 120 | Legal outside-counsel budget line | E3 | Measuring
ILLUSTRATIVE-B2 | Contact-centre summarisation | Agency and overtime hours reduced | Realised cost reduction | Head of Customer Operations | 240 | 60 | Contact-centre agency budget line | E2 | Measuring
ILLUSTRATIVE-B3 | Coding assistant | Contractor hours reduced | Absorbed capacity | Director of Engineering | 108 | 26 | Engineering contractor spend line | E2 | Measuring
ILLUSTRATIVE-B4 | Workforce assistant | Self-reported time saved | Released capacity | COO | 300 | 0 |  | E1 | Expected
ILLUSTRATIVE-B5 | Customer-service agent pilot | Projected chat containment | Avoided cost |  | 90 | 0 |  | E0 | Lapsed
ILLUSTRATIVE-B6 | Contract review assistant | Reviewer time released, not yet absorbed | Released capacity | General Counsel | 0 | 40 |  | E3 | Measuring
ILLUSTRATIVE-B7 | Contact-centre summarisation | Agent time released, not yet converted | Released capacity | Head of Customer Operations | 0 | 180 |  | E2 | Measuring
ILLUSTRATIVE-B8 | Coding assistant | Engineer time released, not yet absorbed | Released capacity | Director of Engineering | 0 | 82 |  | E2 | Measuring

## Summary
Benefit summary (all formulas)
Benefit type | Expected (£k) | Measured (£k)
Realised cost reduction
Revenue or margin
Absorbed capacity
Released capacity
Avoided cost
Risk loss avoided
Total expected (£k)
Realised value that counts (£k)
Share of expected value realised
Measured but not realised: released, avoided or risk (£k)
The illustrative rows are invented and describe no real organisation.

## Evidence levels
Level | Evidence | Good enough for
E0 | Anecdote or expert opinion | Exploration only
E1 | Before and after baseline | An early operational case
E2 | Adjusted baseline or matched cohort | A portfolio decision
E3 | Holdout group or quasi-experiment | A material investment
E4 | Controlled experiment, independently validated | A high-value or high-risk claim
The level is a gate, not a multiplier: no monetised claim below E2.

## Version
Name | AI benefits register
Version | 0.5
Date | 2026-10-08
Status | Proposal from AI Economics Hub. Not a standard.
Change history | 0.5 (2026-10-08): first release.
Related | The AI Value Ledger; the AI portfolio review pack (whose realised value this register supports).
Licence of this template | Free to use. Keep the attribution to AI Economics Hub where the evidence levels are referenced.