## Instructions
AI portfolio review pack
A proposal from AI Economics Hub, version 0.5 (2026-10-08). Not a standard. See the article 'The AI Portfolio Review Pack' (/articles/ai-portfolio-review-pack).
One row per material AI initiative on the Portfolio sheet. Cream cells are inputs. Grey cells are formulas and are locked. The blue rows are ILLUSTRATIVE, with invented figures: overwrite or delete them.
Money is in £ thousands a year, fully loaded: model and consumption, platform, engineering, verification and review, governance, adoption and change, and supplier cost.
Claimed value is what the owner says the initiative is worth. Realised value is what has reached an accepted operational or financial record. Do not enter released time as realised value until it has been absorbed.
Evidence levels E0 to E4 are on the 'Evidence levels' sheet. No monetised claim below E2. The 'Monetised claim allowed?' column applies that rule.
The Decision column is yours to complete. Nothing on these sheets decides for you. The Decision rules sheet gives the tests to apply in the review.
Set the as-at date on the Summary sheet. Reviews dated before it are flagged overdue.
Sheets are protected without a password so you can unprotect to extend them. Nothing leaves your machine.

## Portfolio
ID | Initiative | Function | Business owner (named role) | Annual fully loaded cost (£k) | Claimed annual value (£k) | Realised annual value (£k) | Baseline recorded? (Yes/No) | Evidence level | Risk tier | Strategic importance | Decision | Decision owner | Next review date | Claimed net (£k) | Realised net (£k) | Monetised claim allowed? | Realised share of claim | Review overdue?
ILLUSTRATIVE-1 | Coding assistant | Engineering | Director of Engineering | 98 | 108 | 26 | Yes | E2 | M | M | Hold | Director of Engineering | 2027-01-15
ILLUSTRATIVE-2 | Workforce assistant | All functions | COO | 420 | 300 | 0 | Yes | E1 | M | H | Hold | COO | 2026-12-10
ILLUSTRATIVE-3 | Contact-centre summarisation | Customer operations | Head of Customer Operations | 180 | 240 | 60 | Yes | E2 | M | M | Redesign | Head of Customer Operations | 2027-01-31
ILLUSTRATIVE-4 | Contract review assistant | Legal and procurement | General Counsel | 75 | 160 | 120 | Yes | E3 | H | M | Scale | General Counsel | 2027-03-31
ILLUSTRATIVE-5 | Customer-service agent pilot | Customer operations |  | 60 | 90 | 0 | No | E0 | H | L | Stop | CFO | 2026-09-30

## Summary
Portfolio summary (all formulas except the as-at date)
As-at date (input) | 2026-10-08
Material initiatives
Annualised investment (£k)
Claimed value (£k)
Claimed value that may be monetised, E2 or above (£k)
Realised value (£k)
Realised net position (£k)
Spend at E2 or above (£k)
Share of spend at E2 or above
Spend with no named owner or no baseline (£k)
Reviews overdue
Decision | Initiatives | Annual cost (£k)
Scale
Hold
Redesign
Stop
Undecided
Evidence level | Annual cost (£k)
E0
E1
E2
E3
E4
The illustrative rows are invented and describe no real organisation.

## Agenda
# | Item | What to cover
1 | Movement since the previous review | New, changed and closed initiatives; changes in cost, evidence level and decision.
2 | Cost and forecast variance | Fully loaded cost against forecast, and why it moved.
3 | Evidence movement | Which initiatives gained or lost an evidence level, and what evidence is due.
4 | Material value claims | Claims above the materiality threshold: claimed, realised, and the gap between them.
5 | Risk and autonomy exceptions | Open exceptions, owners and due dates.
6 | Overdue actions | Actions and decisions past their review date.
7 | Decision requests | Scale, hold, redesign or stop recommendations needing a decision, with the funded next action.
8 | Capital and capacity reallocation | Money and scarce capacity released by stops and redesigns, and where it goes.

## Decision rules
Decision | Apply when | What happens
Scale | High value, low load on the binding constraint, and evidence at or above the level the commitment needs. | Fund and extend. Keep measuring.
Hold | Promising, but the evidence is below the level the commitment needs, or ownership or controls are not yet in place. | Keep at current size. Name the evidence that would change the decision, and a date.
Redesign | The outcome is valuable, but the workflow, model route, contract, verification burden or operating model weakens the case. | Relieve the constraint first, then decide again.
Stop | No credible route to acceptable value and risk remains within the agreed decision period. | End it and release the capacity. Record why.

## Evidence levels
Level | Evidence | Good enough for
E0 | Anecdote or expert opinion | Exploration only
E1 | Before and after baseline | An early operational case
E2 | Adjusted baseline or matched cohort | A portfolio decision
E3 | Holdout group or quasi-experiment | A material investment
E4 | Controlled experiment, independently validated | A high-value or high-risk claim
The level is a gate, not a multiplier: no monetised claim below E2.

## Version
Name | AI portfolio review pack
Version | 0.5
Date | 2026-10-08
Status | Proposal from AI Economics Hub. Not a standard.
Change history | 0.5 (2026-10-08): first release.
Related | The AI Value Ledger (the per-workflow record this portfolio view summarises); Scale, hold, redesign, stop.
Licence of this template | Free to use. Keep the attribution to AI Economics Hub where the evidence levels or decision rules are referenced.